## BOQ
RFP / RFQ Reference |  | Date | 2026-06-02
OpCos | Supplier
Terms and Conditions are as per memorandum of understanding or contract
[6 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16
| PROJECT TYPE: Site Improvement - Oversite Aggregates and Concrete |  |  |  | HTA ID | TZTB1217 | HTA ID | TZTB2341 | HTA ID | TZTB2346 | HTA ID | TZTB6750 | HTA ID | TZTB2353 | HTA ID | TZTB1568 | HTA ID | TZTB5713 | HTA ID | TZTB7528 | HTA ID | TZTB7797 | HTA ID | TZTB7519 | HTA ID | TZTB2352 | HTA ID | TZTB3253 | HTA ID | TZDA0495 | HTA ID | TZDA0565 | HTA ID | TZDA1868 | HTA ID | TZDA2939
[5 empty] | Site Name | Nyalaja | Site Name | Mwashina | Site Name | Mabama | Site Name | Milambo Itobo Ucsaf | Site Name | Ndala | Site Name | Tumbi | Site Name | Igunga vtz | Site Name | Itunduru vtz | Site Name | Mwabakima | Site Name | Ndembezi Igunga Vtz | Site Name | Nkinga Sector 0 | Site Name | Usongo Mission | Site Name | Chanika Kitonga | Site Name | Mavurunza G5 | Site Name | Kijitonyama | Site Name | Wazo
[5 empty] | Region | Tabora | Region | Tabora | Region | Tabora | Region | Tabora | Region | Tabora | Region | Tabora | Region | Tabora | Region | Tabora | Region | Tabora | Region | Tabora | Region | Tabora | Region | Tabora | Region | Dar es Salaam | Region | Dar es Salaam | Region | Dar es Salaam | Region | Dar es Salaam
ITEM | Item Description | UNIT | Material Unit Cost (TZS) | Services Unit Cost (TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS) | Qty | TOTAL(TZS)
1 | Site Preparation and Finishing |  |  |  |  | 4771906.405 |  | 3017020.3082 |  | 5091506.0613 |  | 6162354.8361 |  | 5208004.8127 |  | 8263619.8585 |  | 2432583.6061 |  | 2242050.5586 |  | 3998110.4368 |  | 999656.1689 |  | 4363664.6298 |  | 8306590.9425 |  | 3768317.3651 |  | 6360590.8423 |  | 4744447.6963 |  | 10412119.6711
1.1.1 | Retaining Wall including reinforcement beam, stones,bricks,sand and Cement- Not Standard (Not more than 1m) | m³ | 712571.3855 | 355786.5929 |  | 0 |  | 0 | 1.32 | 1410232.5314 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1.8216 | 1946120.8934 |  | 0
1.1.2 | Supply Imported G7 materials and Backfill Site compound, including Compacting to 93% MDD AASHTO (Only the size of the site e.g.10 x 10m). | m³ | 58300 | 9637.3508 | 12.444 | 845412.3936 | 3.8342 | 260485.3905 | 11.7403 | 797601.483 | 18.8012 | 1277302.3615 | 7.0604 | 479664.8717 | 19.4872 | 1323912.1397 | 5.9319 | 402996.5523 | 3.7786 | 256704.6769 | 8.2956 | 563581.0875 | 2.937 | 199531.9994 | 16.0593 | 1091027.6568 | 19.1479 | 1300859.9776 | 17.0946 | 1161361.5418 | 25.4689 | 1730287.8958 | 4.0768 | 276966.4823 | 13.3608 | 907698.7156
1.1.3 | Apply approved herbicide uniformly to prevent future vegetation growth. | Site | 35000 | 0 | 2 | 70000 |  | 0 | 3 | 105000 |  | 0 | 1 | 35000 |  | 0 |  | 0 | 1 | 35000 |  | 0 |  | 0 | 2 | 70000 |  | 0 | 2 | 70000 | 2 | 70000 | 2 | 70000 |  | 0
1.1.4 | Non-woven Geofabric membrane type 250 - 300gsm, UV stabilized, polypropylene or approved equivalent for weed control, (area of membrane required is calculated by removing areas for: tower foundation, plinths, guard hut) (Only the size of the site e.g.15 x 15m) - (Double layer) | m² | 4500 | 1071 | 124.44 | 693255.24 |  | 0 | 117.4025 | 654049.3275 | 188.0118 | 1047413.7378 |  | 0 |  | 0 | 39.5459 | 220310.2089 | 45.7205 | 254708.6548 |  | 0 | 14.685 | 81810.135 | 97.1589 | 541272.1539 |  | 0 | 113.964 | 634893.2824 | 141.4937 | 788261.6812 | 81.5359 | 454236.2204 |  | 0
1.1.5 | Install 19 mm² Stone Chip including mixing in coarse salt within site compound (100 mm layer) (Only the size of the site e.g.10 x 10m) | m³ | 120000 | 11801.5271 | 12.444 | 1640138.2029 |  | 0 | 11.7403 | 1547382.8782 | 18.8012 | 2478024.2348 |  | 0 |  | 0 | 3.9546 | 521221.001 | 4.572 | 602602.5788 |  | 0 | 1.4685 | 193550.5425 | 9.7159 | 1280568.9544 |  | 0 | 11.3964 | 1502062.5409 | 14.1494 | 1864909.2321 | 4.0768 | 537327.4771 |  | 0
1.1.6 | Oversite concrete( wire mesh with concrete of grade C20) - Within Site | m³ | 374325 | 102732.72 |  | 0 | 3.8342 | 1829134.71 |  | 0 |  | 0 | 7.0604 | 3368218.3263 | 12.9915 | 6197695.3694 |  | 0 |  | 0 | 5.5304 | 2638320.0147 |  | 0 |  | 0 | 12.7653 | 6089780.1425 |  | 0 |  | 0 |  | 0 | 16.563 | 7901507.0164
1.1.7 | Oversite concrete( wire mesh with concrete of grade C20) - Outside the Site | m³ | 374325 | 102732.72 | 2.415 | 1152094.3938 | 1.944 | 927400.2077 | 1.21 | 577239.8412 | 2.85 | 1359614.502 | 2 | 954115.44 |  | 0 | 2.7 | 1288055.844 | 2.2912 | 1093034.6481 | 1.669 | 796209.3347 | 1.1 | 524763.492 | 2.8944 | 1380795.8648 | 1.92 | 915950.8224 |  | 0 | 3.22 | 1536125.8584 | 3.06 | 1459796.6232 | 3.36 | 1602913.9392
1.1.8 | Supply Medium Duty Cast Iron Cover and Frame Manhole Cover size 0.8m x 0.8m incl Building of Manhole | ea | 252198.9039 | 118807.2707 | 1 | 371006.1747 |  | 0 |  | 0 |  | 0 | 1 | 371006.1747 | 2 | 742012.3493 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 371006.1747 |  | 0 |  | 0
1.1.9 | Gate Ramp- Steps(stairs) | Site | 300000 | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 400000 |  | 0 |  | 0 |  | 0
2 | Power - Equipment Slab |  |  |  |  | 324946.5137 |  | 2418806.658 |  | 649893.0275 |  | 2058044.4084 |  | 2901913.2893 |  | 1654839.5412 |  | 680000 |  | 0 |  | 2136302.7619 |  | 1117220.8803 |  | 0 |  | 1796302.7619 |  | 873711.5187 |  | 324946.5137 |  | 0 |  | 649893.0275
2.1.1 | Equipment Slab/ Sleepers (ACDB, DCDB, Rectifier Cabinet, Generator, Line Conditioning Unit, Tenant Equipment) Installation - Reinforced concrete | m³ | 534750 | 128415.9 |  | 0 | 1.152 | 763967.1168 |  | 0 | 0.608 | 403204.8672 | 1.216 | 806409.7344 |  | 0 |  | 0 |  | 0 | 1.216 | 806409.7344 | 0.192 | 127327.8528 |  | 0 | 1.216 | 806409.7344 | 0.3375 | 223818.4912 |  | 0 |  | 0 |  | 0
2.1.2 | Installation of complete galvanized standard cable trays (including supply and installation of all accessories/supports and grounding) | Site |  | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
2.1.3 | Install 110mm flexible HDPE Corrugated pipe (with accessories, couplings, etc.) | m | 48070 | 6087.7523 | 6 | 324946.5137 | 18 | 974839.5412 | 12 | 649893.0275 | 18 | 974839.5412 | 24 | 1299786.0549 | 18 | 974839.5412 |  | 0 |  | 0 | 12 | 649893.0275 | 12 | 649893.0275 |  | 0 | 12 | 649893.0275 | 12 | 649893.0275 | 6 | 324946.5137 |  | 0 | 12 | 649893.0275
2.1.4 | Earthing System for HTA + 2 Tenant Greenfield Site (Standard Design) complete for a 15m x 15m site layout. | lot | 530000 | 150000 |  | 0 | 1 | 680000 |  | 0 | 1 | 680000 | 1 | 680000 | 1 | 680000 | 1 | 680000 |  | 0 | 1 | 680000 | 0.5 | 340000 |  | 0 | 0.5 | 340000 |  | 0 |  | 0 |  | 0 |  | 0
2.1.5 | Supply and installation of earth rods and accessories | each | 115717.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 115717.5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Project Management & Documentation |  |  |  |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802 |  | 779902.802
3.1.1 | Technical Site Survey, Project Management, Field Supervision and Administrative costs including QA, Integration management and handover | Site |  | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802 | 1 | 779902.802
| SUBTOTAL |  |  |  |  | 5876755.7207 |  | 6215729.7682 |  | 6521301.8908 |  | 9000302.0465 |  | 8889820.904 |  | 10698362.2017 |  | 3892486.4081 |  | 3021953.3606 |  | 6914316.0007 |  | 2896779.8511 |  | 5143567.4318 |  | 10882796.5064 |  | 5421931.6859 |  | 7465440.158 |  | 5524350.4983 |  | 11841915.5006
| SUBTOTAL |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Transport, Haulage and Mobilization
5.1.1 | Transportation of materials to site (Within Dar es Salaam) | km |  | 3475 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 347500 | 100 | 347500 | 100 | 347500 | 100 | 347500
5.1.2 | Transportation of materials to site (Outside Dar es Salaam) | km |  | 4120 | 150 | 618000 | 120 | 494400 | 100 | 412000 | 200 | 824000 | 100 | 412000 | 900 | 3708000 | 822 | 3386640 | 100 | 412000 | 100 | 412000 | 100 | 412000 | 100 | 412000 | 100 | 412000 |  | 0 |  | 0 |  | 0 |  | 0
| SUBTOTAL |  |  |  |  | 618000 |  | 494400 |  | 412000 |  | 824000 |  | 412000 |  | 3708000 |  | 3386640 |  | 412000 |  | 412000 |  | 412000 |  | 412000 |  | 412000 |  | 347500 |  | 347500 |  | 347500 |  | 347500
[5 empty] | SUB TOTAL (TZS) | 6494755.7207 | SUB TOTAL (TZS) | 6710129.7682 | SUB TOTAL (TZS) | 6933301.8908 | SUB TOTAL (TZS) | 9824302.0465 | SUB TOTAL (TZS) | 9301820.904 | SUB TOTAL (TZS) | 14406362.2017 | SUB TOTAL (TZS) | 7279126.4081 | SUB TOTAL (TZS) | 3433953.3606 | SUB TOTAL (TZS) | 7326316.0007 | SUB TOTAL (TZS) | 3308779.8511 | SUB TOTAL (TZS) | 5555567.4318 | SUB TOTAL (TZS) | 11294796.5064 | SUB TOTAL (TZS) | 5769431.6859 | SUB TOTAL (TZS) | 7812940.158 | SUB TOTAL (TZS) | 5871850.4983 | SUB TOTAL (TZS) | 12189415.5006
[5 empty] | +18% VAT | 1169056.0297 | +18% VAT | 1207823.3583 | +18% VAT | 1247994.3403 | +18% VAT | 1768374.3684 | +18% VAT | 1674327.7627 | +18% VAT | 2593145.1963 | +18% VAT | 1310242.7535 | +18% VAT | 618111.6049 | +18% VAT | 1318736.8801 | +18% VAT | 595580.3732 | +18% VAT | 1000002.1377 | +18% VAT | 2033063.3711 | +18% VAT | 1038497.7035 | +18% VAT | 1406329.2284 | +18% VAT | 1056933.0897 | +18% VAT | 2194094.7901
[5 empty] | TOTAL (TZS) | 7663811.7504 | TOTAL (TZS) | 7917953.1265 | TOTAL (TZS) | 8181296.2311 | TOTAL (TZS) | 11592676.4148 | TOTAL (TZS) | 10976148.6667 | TOTAL (TZS) | 16999507.398 | TOTAL (TZS) | 8589369.1616 | TOTAL (TZS) | 4052064.9655 | TOTAL (TZS) | 8645052.8808 | TOTAL (TZS) | 3904360.2243 | TOTAL (TZS) | 6555569.5695 | TOTAL (TZS) | 13327859.8775 | TOTAL (TZS) | 6807929.3893 | TOTAL (TZS) | 9219269.3865 | TOTAL (TZS) | 6928783.588 | TOTAL (TZS) | 14383510.2907
[5 empty] | Service | 5876755.7207 | Service | 6215729.7682 | Service | 6521301.8908 | Service | 9000302.0465 | Service | 8889820.904 | Service | 10698362.2017 | Service | 3892486.4081 | Service | 3021953.3606 | Service | 6914316.0007 | Service | 2896779.8511 | Service | 5143567.4318 | Service | 10882796.5064 | Service | 5421931.6859 | Service | 7465440.158 | Service | 5524350.4983 | Service | 11841915.5006
[5 empty] | Transport | 618000 | Transport | 494400 | Transport | 412000 | Transport | 824000 | Transport | 412000 | Transport | 3708000 | Transport | 3386640 | Transport | 412000 | Transport | 412000 | Transport | 412000 | Transport | 412000 | Transport | 412000 | Transport | 347500 | Transport | 347500 | Transport | 347500 | Transport | 347500
#REF!
Note on F12: Salim Buheti: Derived from retainwall shiett
Note on O12: user: Retaining wall repair Retaining wall support
Note on X12: user: stone pitching repair
Note on F15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HTT to negotiate with Nabaki
Note on I18: user: Outside concrete Cable tray support SLEEPERS repair
Note on L18: user: Outside concrete
Note on O18: user: Beam repair slab repair
Note on AA18: user: outside concrete Wall plastering and repair
Note on AD18: user: outside concrete Wall plastering
Note on U22: user: 3new tenants
Note on AA22: user: 2new tenants
Note on I24: user: Cables passing through generator slab need to be covered
Note on U26: user: constructed Manhole

## Summary
S/n | Description | Site Name | Site ID | Qty | Services (TZS) | Transportation (TZS) | Total Price (TZS)
1 | Site improvement works | Nyalaja | TZTB1217 | 1 | 5876755.7207 | 618000 | 6494755.7207
2 | Site improvement works | Mwashina | TZTB2341 | 1 | 6215729.7682 | 494400 | 6710129.7682
3 | Site improvement works | Mabama | TZTB2346 | 1 | 6521301.8908 | 412000 | 6933301.8908
4 | Site improvement works | Milambo Itobo Ucsaf | TZTB6750 | 1 | 9000302.0465 | 824000 | 9824302.0465
5 | Site improvement works | Ndala | TZTB2353 | 1 | 8889820.904 | 412000 | 9301820.904
6 | Site improvement works | Tumbi | TZTB1568 | 1 | 10698362.2017 | 3708000 | 14406362.2017
7 | Site improvement works | Igunga vtz | TZTB5713 | 1 | 3892486.4081 | 3386640 | 7279126.4081
8 | Site improvement works | Itunduru vtz | TZTB7528 | 1 | 3021953.3606 | 412000 | 3433953.3606
9 | Site improvement works | Mwabakima | TZTB7797 | 1 | 6914316.0007 | 412000 | 7326316.0007
10 | Site improvement works | Ndembezi Igunga Vtz | TZTB7519 | 1 | 2896779.8511 | 412000 | 3308779.8511
11 | Site improvement works | Nkinga Sector 0 | TZTB2352 | 1 | 5143567.4318 | 412000 | 5555567.4318
12 | Site improvement works | Usongo Mission | TZTB3253 | 1 | 10882796.5064 | 412000 | 11294796.5064
13 | Site improvement works | Chanika Kitonga | TZDA0495 | 1 | 5421931.6859 | 347500 | 5769431.6859
14 | Site improvement works | Mavurunza G5 | TZDA0565 | 1 | 7465440.158 | 347500 | 7812940.158
15 | Site improvement works | Kijitonyama | TZDA1868 | 1 | 5524350.4983 | 347500 | 5871850.4983
16 | Site improvement works | Wazo | TZDA2939 | 1 | 11841915.5006 | 347500 | 12189415.5006
0
[5 empty] | 110207809.9334 | 13305040 | 123512849.9334